## Sheet1
Project planning and user stories | Planning of project |  | 4
Research of JavaFX GUI | Research Java FX GUI |  | 6
Interviews of EON Gamemasters | Planning of project |  | 4
Project planning continued | Planning of project |  | 4
Research of JavaFX GUI | Research Java FX GUI |  | 12 | Planning of project | 12
Implementation of Basic UI | Implementation of basic GUI |  | 4 | Research Java FX GUI | 18
Project planning continued | Planning of project |  | 0 | Implementation of basic GUI | 52
Research of JavaFX GUI and interaction with menues | Research Java FX GUI |  | 0 | Research MS Access databases | 4
Implementation of Basic UI | Implementation of basic GUI |  | 0 | Data input into MS Access database | 28
Research of H2 Database | Research MS Access databases |  | 0 | Implementation of MS Access databases for project | 16
Project planning continued | Planning of project |  | 0 | Implementation of generator functionality | 16
Research of JavaFX GUI and interaction with menues | Research Java FX GUI |  | 0 | Research iText and PDFbox | 5
Implementation of Basic UI | Implementation of basic GUI |  | 0 | Implementation of PDF creator | 21
Research of H2 Database | Research MS Access databases |  | 0 | Test plan and execution | 84
|  |  |  | Finishing touches | 10
Switch from H2 to Accdb and research | Research MS Access databases |  | 4
Construction of base tables | Data input into MS Access database |  | 8
Switch to multiscene JavaFX | Implementation of basic GUI |  | 8
Finishing implementation of JavaFX GUI | Implementation of basic GUI |  | 12 | Total Time spent | 266
Finishing database tables | Data input into MS Access database |  | 8
Finishing database tables | Data input into MS Access database |  | 4
Implementing Databases connection and JavaFX data transfer between scenes | Implementation of MS Access databases for project |  | 16
Implementation of generator functionality | Implementation of generator functionality |  | 8
Finishing database tables | Data input into MS Access database |  | 8
JavaFX data transfer between scenes | Implementation of basic GUI |  | 0
Implementation of generator functionality | Implementation of generator functionality |  | 8
Populating JavaFX tables and implementing altering functionality | Implementation of basic GUI |  | 12
Research and implementation of PDF function | Research iText and PDFbox | Implementation of PDF creator | 10
JavaFX data transfer between scenes | Implementation of basic GUI |  | 4
Populating JavaFX tables and implementing altering functionality | Implementation of basic GUI |  | 12
Research and implementation of PDF function continued | Implementation of PDF creator |  | 8
Creation of PDF template | Implementation of PDF creator |  | 8
Constructing testplan | Test plan and execution |  | 0
Creating automated test cases | Test plan and execution |  | 0
Executing manual tests | Test plan and execution |  | 4
Deploying executable JAR for betatesting | Test plan and execution |  | 2
bug fixing from testing response | Test plan and execution |  | 16
Constructing testplan | Test plan and execution |  | 2
Creating automated test cases | Test plan and execution |  | 0
Executing further manual tests | Test plan and execution |  | 4
Deploying executable JAR(conversion to exe and dmg for betatesting | Test plan and execution |  | 6
bug fixing from testing response | Test plan and execution |  | 6
Restructure and Refactoring | Test plan and execution |  | 8
Constructing testplan | Test plan and execution |  | 2
Creating automated test cases | Test plan and execution |  | 0
Executing further manual tests | Test plan and execution |  | 6
bug fixing from testing response | Test plan and execution |  | 6
Creating automated test cases | Test plan and execution |  | 16
Executing further manual tests | Test plan and execution |  | 6
Making instructions video and demo(English and Swedish) | Finishing touches |  | 2
Creating Post mortem and finishing report | Finishing touches |  | 8